## Checklist
Item to be checked | Status | Notes
Put the database is backup mode before getting the trace file and transferring data files.
Verify the size of the datafiles matches between ecpna and ec1pna after the transfer.
Verify if the ecpna database backup mode has ended.
Modify the ecpna rman archive delete script to save a day worth of archive logs.
Verify that all the archive logs were saved since the ecpna database was in backup mode.
Verify the trace file has commented out RECOVER DATABASE and alter db open resetlogs lines.
Verify if the pfile transferred from ecpna to ec1pna is current.
Check for the typos on the datafile naming after transfer and correct them.
Notify team to not add any datafiles on ecpna database.
Add a test user and test table on ecpna before transferring the last log file for testing.
Be sure to switch the logfile and grab the last log file after ending the database backup mode.
Create pfile from spfile on source database, ecpna and move it to ec1pna.
Make sure that the trace sql file on ec1pna has mention of pfile location.
Make sure of CREATE CONTROLFILE SET command instead of REUSE in the trace sql file.
Once you run the trace sql file, be sure to check the alert log for any errors.
while running the recover database until cancel verify if all the archive logs are applied before open resetlogs.
Add temp tablespace after alter database open resetlogs
Create spfile from pfile on ec1pna.
modify the memory parameters [Consult Ned].
Modify the log_archive_format on ec1pna.
Be sure to have 3 times the time before actual cut-over that you are just applying archive logs on ec1pna
At the start of the Migration change window, lock the accounts on ecpna database, shutdown listener, shutdown immediate, startup restrict, and check / copy any delta archive logs.
Add the ecpna database entries to the new Ec1pna database.
Modify the listener.ora file on ec1pna to have ecpna entry so that old entries point to new database.
Check with different app teams that the connectivity is working to the new database.