## Checklist
Task ID | Task | Completed | Notes
Preliminary DB Migration Tasks
Set up listener.ora on new server to include global_dbname of ecpna.
Search all servers for tnsnames.ora references to this database. Prepare plan to update tnsnames.ora files.
Search all database for hardcoded DB links to the ECPNA database.
Create admin directory structure on new server.
Source DB: Set database to force logging mode
Check for special one-off patches on the source DB side.
Check for external tables on the source DB side.
Preliminary Tasks to get set up
Create a new create controlfile script (create_control.sql)
Verify create controlfile script *only* creates the controlfile, and does not startup or recover or open the database
Verify create controlfile script sets the NEWNAME for the database
Create a script to add the tempfiles to the temp tablespace (tempfiles.sql).
Create new pfile script with correct memory parameters, etc.
Create new password file.
Create new wallet.
Create a script to copy the database files to the new server (copy_datafiles.sh) Note: If any DB files need to be renamed for consistency, do so in the script.
Create ssh keys to allow copy of database files and archivelogs without passwd authentication
Create a command to copy the archivelogs across to the new server in the right place: scp *.arc plec1vmdb02:/usr/app/oracle/admin/ec1pna/archive/
Get a second person to verify your scripts above.
Notify DBA team not to add datafiles on the old database (ecpna).
Modify the ecpna rman archive delete script to save a day worth of archive logs on disk.
Check for special cron jobs on the source DB side.
Database Replication and Test Recovery Tasks
alter database begin backup
scp the database files across
Verify the size of the datafiles match between ecpna and ec1pna after the transfer.
scp the archivelogs across
Verify that there were *not* any DB files recently added to the database
startup nomount pfile=/usr/app/oracle/product/11.2.0.4/dbs/initec1pna.ora
Run the create controlfile script on ec1pna (create_control.sql) Again, verify that there is no recovery or alter database open in the script.
Roll forward at least one archivelog and verify alert log recover database until cancel using backup controlfile; Look for this string in the alert log to verify: xxxxxxxxxxxxxxxxxxxx
Check alert log for errors.
If DB recovery successful, only then end backup mode on source: alter database end backup;
Note: Be sure to have 3 times the time it took to copy over all of the DB files before actual cut-over. During this time, you are just copying over and applying archive logs on ec1pna to keep it up to date.
Tasks to Perform Just before the Change Window
Verify that there were *not* any DB files recently added to the database
Verify that there were no recent init.ora parameters changed.
Copy archivelogs across and recover and check for success in the alert log. Look for this string in the alert log to verify: xxxxxxxxxxxxxxxxxxxx
Tasks to Perform During the CR Window to Finish Recovering and Opening the DB
Restrict crons on both source and target sides
Create blackouts
Shutdown application
shutdown the listener
startup force (to kill all application sessions)
Create table and a row to mark the last transaction in the database: drop table odba.end_marker; create table odba.end_marker (last_heartbeat date); insert into odba.end_marker(last_heartbeat) values (sysdate); commit;
shutdown abort; startup restrict; alter system switch logfile; alter database archivelog current;
Copy archivelogs across and recover and check for success in the alert log. Look for this string in the alert log to verify: xxxxxxxxxxxxxxxxxxxx
While running the recover database until cancel verify if all the archive logs are applied before open resetlogs.
Check alert log for errors.
alter database open resetlogs;
Check alert log for errors.
Verify that the last transaction made it over: select to_char(last_heartbeat,'YYYY-MON-DD HH24:MI:SS') from odba.end_marker;
Check v$datafile_header and v$tempfile to make sure all files have status = 'ONLINE'
Modify the log_archive_format on ec1pna to use the new SID name (it was left as ecpna to ease the recovery).
Run script to add tempfiles to temp tablespace (tempfiles.sql).
Create spfile from pfile and restart DB to check it.
Check alert log for errors.
Update tnsnames.ora files on all servers to point to new DB.
Start listener and verify connectivity.
Verify wallet is in place and get app team to test it after opening to users.
Allow users to connect.
Configure database monitoring on new Target DB.
Configure OEM on new Target DB.
Configure and test backups for new Target DB.
Re-enable cron jobs for database.
Remove blackouts (but not the blackout on the redhat cluster service)