## Oracle Log Shipping Migration
Oracle Log Shipping Migration Steps Last Updated: Dec 21, 2015 (version 1)
Pre-Migration Stage
Task ID | Task | Ownership | Applicable | Notes
1 | Work with System Admin and Storage Teams to build target server, configure hardware and networking on new DB server. | Avaya DBA | Always
2 | Install RDBMS software, patches, harden server. | Avaya DBA | Always
3 | Deliver target server to HPE with software installed, server hardened, listener running. | Avaya DBA | Always
4 | Configure all OS level jobs on database server. | Avaya DBA | Always
5 | Provide SQL to determine which accounts to lock upon migration (and unlock in the case of a "No Stay" decision). See Avaya provided script lock_all_accounts.sql | Avaya DBA | Always
6 | Create admin directory structure on new server. | Avaya DBA | Always
7 | Source DB: Set database to force logging mode | Avaya DBA | Always
8 | NFS mount target server oradata and archive filesystems on the ftp server (dldbavmdb13 or pldbnvmdb01). | HPE | Always
9 | Check for kernel parameters as per standard doc process | HPE | Always | Redundant? Already performed by Avaya DBA.
10 | Check for required packages, dependencies | HPE | Always | Redundant? Already performed by Avaya DBA.
11 | Run pre-migration script for information from Source Database - READ ONLY Scripts | HPE | Always
12 | Copy database configuration files across: spfile, password file, etc. | HPE | Always
13 | Generate ftp script: Script will compress datafiles and then ftp them to Target Server. | HPE | Always
14 | Generate create controlfile script for Target DB. | HPE | Always
15 | Generate script to create tempfiles on Target DB. | HPE | Always
16 | External Tables - Source Database (Check & Collect) | HPE | Always
17 | Hot Copy of database across network: | HPE | Always
18 | Notify Avaya DBA team that hot copy is starting | HPE | Always
19 | Source DB: Set RMAN archivelog backup to not delete archivelogs. | HPE | Always
20 | Source DB: Begin Backup Mode | HPE | Always
21 | Source DB: Begin script to compress and transfer datafiles | HPE | Always
22 | Check the ftp logs carefully for errors | HPE | Always
23 | Manually send any datafiles that may have failed to be transferred successfully | HPE | Always
24 | gunzip datafiles on Target DB Server. | HPE | Always
25 | Verify that all datafiles are across successfully before ending backup mode on Source DB. * Verify by datafile name and bytes | HPE | Always
26 | Source DB: End Backup Mode | HPE | Always
27 | Target DB: Run prepared script to create new DB Controlfile. | HPE | Always
28 | Periodically repeat these 3 steps to recover Target DB up to current. Proceed with opening database when ready. | HPE | Always
29 | 1. ftp the latest archivelogs to the target server. | HPE | Always
30 | 2. Target DB: Recover database until cancel using backup controlfile; | HPE | Always
31 | 3. Source DB: Remove archivelogs that have been applied on target. | HPE | Always
32 | Target DB: Alter database open resetlogs | HPE | On Dry Run
33 | Target DB: Run prepared script to add tempfiles | HPE | On Dry Run
34 | Check for errors in the recovery session and in the alert log. | HPE | On Dry Run
35 | Run @catbundle psu apply as sysdba | HPE | On Dry Run
36
37 | Notify Avaya DBA so that they can continue with the steps below. | HPE | Always
38 | Configure database monitoring on new Target DB. | Avaya DBA | Always
39 | Configure OEM on new Target DB. | Avaya DBA | Always
40 | Configure and test backups for new Target DB. | Avaya DBA | Always
41
42 | Prepare Environment for Actual Go Live | HPE | Prepare for Live Cutover
43 | Wipe test copy of database, and repeat steps to refresh database files from current production approx ~1-2 days before the scheduled true migration/cutover. | HPE | Prepare for Live Cutover
44 | Target DB: Disable cron jobs for database. | HPE | Prepare for Live Cutover
45 | Target DB: Black out monitoring. 1) Create OEM blackout using the GUI. 2) touch /tmp/DISABLE_OVO file to black out OVO Process Monitoring. * Instructions provided by Avaya as needed. | HPE | Prepare for Live Cutover
46 | Repeat steps above to refresh database files from production, but do not open the database resetlogs (i.e. stop at step # X) | HPE | Prepare for Live Cutover
47 | Verify that no datafiles were added to database since the ftp and create controlfile scripts were originally generated. Update scripts if necessary. | HPE | Prepare for Live Cutover
48 | Verify the sizing of the tempfiles in the previously generated create tempfile script. Update tempfile script if necessary. |  | Prepare for Live Cutover
49
Migration Stage
Task ID | Task | Ownership | Applicable
1 | Target DB: Disable cron jobs for database. | HPE | Always
2 | Target DB: Black out monitoring. 1) Create OEM blackout using the GUI. 2) touch /tmp/DISABLE_OVO file to black out OVO Process Monitoring. * Instructions provided by Avaya as needed. | HPE | Always
3 | Target DB: Stop the listener | HPE | Always
4 | Target DB: alter system set job_queue_processes=0 scope=both; | HPE | Always
5 | Source DB: Disable RMAN backups (place an "exit 0" at the top of the ONL and ARC scripts). This is to prevent errors while the Source DB is down. * Instructions provided by Avaya as needed | HPE | Only on Real Cutover
6 | Source DB: Disable cron jobs for database. | HPE | Only on Real Cutover
7 | Source DB: Black out monitoring. 1) Create OEM blackout using the GUI. 2) touch /tmp/DISABLE_OVO file to black out OVO Process Monitoring. 3) touch db_maint file to to put RHCS in Maintenance Mode. * Instructions provided by Avaya as needed. | HPE | Only on Real Cutover
8 | *** Beginning of Database Outage Here ***
9 | Source DB: Stop the listener | HPE | Only on Real Cutover
10 | Source DB: alter system set job_queue_processes=0 scope=both; | HPE | Only on Real Cutover
11 | Source DB: Bounce DB, switch logfile, shutdown immediate. | HPE | Only on Real Cutover
12 | ftp the latest archivelogs to the target server. | HPE | Always
13 | Target DB: Recover database until cancel using backup controlfile; | HPE | Always
14 | Target DB: Alter database open resetlogs | HPE | Always
15 | Target DB: Run prepared script to add tempfiles | HPE | Always
16 | Check for errors in the recovery session and in the alert log. | HPE | Always
17 | Run @catbundle psu apply as sysdba | HPE | Always
| Check v$datafile_header and v$tempfile to make sure all files have status = 'ONLINE' | HPE | Always
18 | Run utlrp.sql script to recompile the invalid objects. | HPE | Always
19 | External Tables - Target Database - Normal ftp transfer to Target with same directory structure. External Tables not commonly used at Avaya, but if there is a directory structure, use a tarball to transfer. | HPE | Always
20 | Run post-migration script for information from Target Database - READ ONLY Scripts | HPE | Always | May not be required since this is log shipping.
21 | Compare and verify target and source database schema and object counts | HPE | Always | May not be required since this is log shipping.
22 | Check database sizes,data files,corruptions(if any),alert logs,opatch inventory list | HPE | Always | May not be required.
23 | Verify Listener Status, Network Status, TNS entries for DB Links. | HPE | Always
24 | Verify environment variables and check if anything is missing or pointed incorrectly | HPE | Always | Redundant? Already performed by Avaya DBA.
25 | Verify oratab entries and Oracle Base,Oracle Home locations | HPE | Always | May not be required since this is log shipping.
26 | Target DB: alter system set job_queue_processes=10 scope=both; | HPE | Always
27 | Target DB: Restart the listener and verify no errors when connecting remotely. | HPE | Always
28 | *** End of Database Outage Here ***
29
30 | Notify Avaya DBA so that they can continue with the steps below. | HPE | Always
31 | Target DB: Configure database monitoring on new Target DB. | Avaya DBA | Always
32 | Target DB: Configure OEM on new Target DB. | Avaya DBA | Always
33 | Target DB: Configure and test backups for new Target DB. | Avaya DBA | Always
34 | Target DB: Re-enable cron jobs for database. | Avaya DBA | Always
35
36 | Target DB: Remove HP OVO blackout (remove /tmp/DISABLE_OVO file). * Instructions provided by Avaya as needed. | HPE | Always
37 | Source DB: Restart DB and lock the DB users as captured above. This is to prevent and to log connection attempts to the original database, after the migration is completed. | HPE | Only on Real Cutover
38 | Source DB: Restart the listener (accounts are all locked as per the item above). | HPE | Only on Real Cutover
39 | Source DB: Re-enable RMAN Online backups (remove "exit 0" at the top of the scripts). * Instructions provided by Avaya as needed | HPE | Only on Real Cutover
40 | Source DB: Re-enable cron jobs for database. | HPE | Only on Real Cutover
41 | Source DB: Remove Monitoring Blackouts. 1) Remove OEM blackout using the GUI. 2) Remove /tmp/DISABLE_OVO file. 3) Remove db_maint file. * Instructions provided by Avaya as needed. | HPE | Only on Real Cutover
42 | Repoint Remote App Servers: On Application Servers and other DB Servers that connect to this DB, repoint tnsnames.ora files, jdbc strings, ODBC datasources, etc. to point to the new database. In some cases this will be the new App servers that were migrated, but in other cases these may be servers that are still in US1. | Avaya App Teams | Always
43 | Conduct Application Integration and Testing. | Avaya App Teams | Always
44
Stay / No-Stay Decision and Rollback Plan
Task ID | Task | Ownership | Applicable
| Summary of Approach for the Database Tier regarding a Stay/No-Stay Decision: 1) If Stay/No-Stay decision is to “Stay”, accounts on the Source DB remain locked. This will allow us to detect connection attempts to the old database. 2) If Stay/No-Stay decistion is “No-Stay” (rollback), then the same accounts will be unlocked by HPE for the rollback to the original source DB. | HPE | Rollback
1 | (No-Stay) Source DB: Unlock DB Users on Source DB using DDL captured beforehand. | HPE | Rollback
2 | (No-Stay) Target DB: Lock DB Users on Target DB using DDL captured beforehand. This is to prevent and to log connection attempts to the new, Target database, after the rollback is completed. | HPE | Rollback
3 | (No-Stay) Source DB: alter system set job_queue_processes=10 scope=both; | HPE | Rollback
4
Post-Migration Stage
Task ID | Task | Ownership | Applicable
1 | HPE will check for connection attempts to the old database 1 day and 5 days after the migration, just to make sure that everything was repointed. Any connection attempts found will be reported to the Application Teams. | HPE | Always
2 | Source DB Retirement | Avaya DBA | Always
3 | umount and unshare NFS mounted oradata file system from the ftp server. | HPE | Always
4
5